## 2.2 Totex costs summary
Regulatory Reporting Pack
Cadent East of England
2017/18
2.2 Summary of totex costs
Current year RRP submission - £m
2017/18 prices
| Actuals |  |  |  | Current year actuals | Forecast |  |  | Forecast RIIO Total
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
LTS, storage and entry | 7.0586 | 9.65 | 9.4417 | 8.6362 | 12.0328 | 19.8122 | 25.6435 | 22.065 | 114.34
Connections | 10.5681 | 11.7417 | 12.8173 | 14.5477 | 17.2821 | 17.5 | 17.5 | 17.5 | 119.457
Mains Reinforcement | 1.7224 | 1.4626 | 1.8264 | 1.491 | 6.4339 | 16.5918 | 4.3907 | 4.9679 | 38.8867
Governors (Replacement) | 1.0361 | 1.1638 | 1.0561 | 1.6693 | 1.1987 | 4.5914 | 6.9661 | 6.2658 | 23.9472
Other Capex | 22.4055 | 25.3991 | 21.3689 | 20.7245 | 21.8351 | 22.9296 | 32.8853 | 12.6866 | 180.2345
of which IT | 14.7528 | 12.2964 | 9.1731 | 5.4313 | 3.577 | 6.8257 | 10.8538 | 5.659 | 68.5692
of which Vehicles | 2.1161 | 2.7337 | 2.4608 | 4.6255 | 6.7104 | 4.6755 | 2.0636 | 2.7183 | 28.1039
Total Capex | 42.7907 | 49.4172 | 46.5105 | 47.0685 | 58.7825 | 81.425 | 87.3856 | 63.4853 | 476.8653
HSE driven mains & services | 95.1491 | 93.3655 | 94.0241 | 81.8174 | 84.9376 | 101.0056 | 116.8882 | 97.2011 | 764.3886
Non-HSE driven mains & services | 7.4131 | 14.7627 | 20.6235 | 18.8588 | 21.2026 | 23.6067 | 28.4768 | 28.1899 | 163.1342
Risers | 0.61437 | 3.0914 | 2.0065 | 1.0872 | 1.3479 | 0.96452 | 4.2553 | 5.0971 | 18.4643
Total Repex | 103.1766 | 111.2196 | 116.6542 | 101.7634 | 107.4881 | 125.5769 | 149.6202 | 130.4882 | 945.9871
Work Management | 64.9407 | 37.4307 | 32.1199 | 31.9375 | 29.8526 | 29.5922 | 28.9844 | 27.3559 | 282.214
Emergency | 17.5188 | 18.3817 | 16.8357 | 18.8283 | 18.7487 | 18.4793 | 17.4745 | 16.7286 | 142.9957
Repair | 16.2105 | 17.7161 | 16.9065 | 26.3649 | 22.4684 | 20.5484 | 19.8549 | 18.7581 | 158.8278
Maintenance | 24.6609 | 24.8435 | 28.8654 | 30.9629 | 30.2959 | 31.1213 | 32.9614 | 30.2243 | 233.9355
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Activities | 10.4761 | 12.4832 | 10.7403 | 10.7366 | 9.146 | 10.6657 | 10 | 9.6199 | 83.8678
of which xoserve | 6.7293 | 7.4615 | 6.8915 | 5.9668 | 4.2682 | 6.9109 | 6.0704 | 5.6356 | 49.9342
Total Direct Opex | 133.8072 | 110.8552 | 105.4678 | 118.8302 | 110.5117 | 110.4067 | 109.2752 | 102.6867 | 901.8406
Business support | 45.3593 | 45.3367 | 42.8745 | 41.6237 | 33.8161 | 31.2771 | 29.9748 | 28.2886 | 298.5508
Training & Apprentices | 2.044 | 4.6494 | 6.7811 | 7.5022 | 8.8686 | 9.5475 | 7.8706 | 7.393 | 54.6565
Total Indirect Opex | 47.4033 | 49.9861 | 49.6556 | 49.1259 | 42.6847 | 40.8245 | 37.8455 | 35.6817 | 353.2073
Total Opex | 181.2104 | 160.8413 | 155.1235 | 167.9561 | 153.1964 | 151.2313 | 147.1206 | 138.3684 | 1255.0479
Of which total sub-deducts | 0.091679 | 0.012369 | 0.015962 | 0.0043599 | 0.0043528 | 0 | 0 | 0
Total Controllable costs | 327.1778 | 321.478 | 318.2881 | 316.788 | 319.467 | 358.2331 | 384.1264 | 332.3418 | 2677.9003
Non-Controllable costs
Licence/network/other | 72.523 | 77.1417 | 77.2446 | 77.4984 | 83.4393 | 85.0708 | 83.956 | 83.0418 | 639.9157
NTS exit costs | 29.2716 | 27.4711 | 24.549 | 25.7042 | 25.4264 | 19.303 | 24.5782 | 26.1512 | 202.4547
Shrinkage | 11.7063 | 8.7812 | 6.0157 | 5.9416 | 6.701 | 7.7093 | 6.0515 | 5.3229 | 58.2295
NTS pensions contributions | 8.2221 | 8.3902 | 11.6398 | 11.4548 | 7.1014 | 7.1056 | 0 | 0 | 53.914
Total non-controllable costs | 121.723 | 121.7842 | 119.4491 | 120.5991 | 122.6681 | 119.1887 | 114.5857 | 114.516 | 954.5138
Total funded costs - including uncertainties | 448.9008 | 443.2622 | 437.7372 | 437.3871 | 442.1352 | 477.4218 | 498.7121 | 446.8578 | 3632.4142
Of which: uncertainties*:
Smart metering | 0.098504 | 0.18343 | 0.41747 | 0.89106 | 2.6852 | 4.141 | 6.2957 | 3.8736 | 18.586
Streetworks | 2.4025 | 5.8122 | 6.7726 | 5.5125 | 6.6342 | 5.4811 | 8.1185 | 8.8867 | 49.6204
Physical Security Upgrade Programme (PSUP) | -1.464 | 0.38692 | 0.3828 | 0.39737 | 3.4765 | 7.266 | 16.3325 | 0 | 26.7782
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total uncertainties* | 1.037 | 6.3826 | 7.5729 | 6.801 | 12.7959 | 16.8882 | 30.7467 | 12.7604 | 94.9846
Total funded costs - excluding uncertainties* | 447.8637 | 436.8796 | 430.1643 | 430.5861 | 429.3392 | 460.5337 | 467.9654 | 434.0974 | 3537.4295
Previous year RRP submission - £m | [10 empty] | Variance from previous year | [9 empty] | % Variance from previous year
2017/18 prices
| Actuals |  |  |  |  | Forecast
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
LTS, storage and entry | 7.0586 | 9.65 | 9.4417 | 8.6362 | 10.8458 | 12.2605 | 14.9377 | 11.3841 | 84.2146 |  | LTS, storage and entry | 0 | 0 | 0 | 0 | 1.1869 | 7.5517 | 10.7057 | 10.681 | 30.1253 | LTS, storage and entry | 0% | 0% | 0% | 0% | 10.94% | 61.59% | 71.67% | 93.82% | 35.77%
Connections | 10.5681 | 11.7417 | 12.8173 | 14.5477 | 11.5831 | 11.6681 | 11.3675 | 11.1977 | 95.4913 |  | Connections | 0 | 0 | 0 | 0 | 5.6991 | 5.8319 | 6.1325 | 6.3023 | 23.9657 | Connections | 0% | 0% | 0% | 0% | 49.2% | 49.98% | 53.95% | 56.28% | 25.1%
Mains Reinforcement | 1.7224 | 1.4626 | 1.8264 | 1.491 | 4.527 | 4.6684 | 6.2764 | 7.0545 | 29.0287 |  | Mains Reinforcement | 0 | 0 | 0 | 0 | 1.9069 | 11.9235 | -1.8857 | -2.0866 | 9.858 | Mains Reinforcement | 0% | 0% | 0% | 0% | 42.12% | 255.4% | -30.04% | -29.58% | 33.96%
Governors (Replacement) | 1.0361 | 1.1638 | 1.0561 | 1.6693 | 4.2426 | 4.505 | 4.2655 | 4.6222 | 22.5605 |  | Governors (Replacement) | 0 | 0 | 0 | 0 | -3.0439 | 0.086422 | 2.7006 | 1.6435 | 1.3867 | Governors (Replacement) | 0% | 0% | 0% | 0% | -71.75% | 1.918% | 63.31% | 35.56% | 6.146%
Other Capex | 22.4055 | 25.3991 | 21.3689 | 20.7245 | 31.289 | 38.9364 | 28.3725 | 19.0161 | 207.5119 |  | Other Capex | 0 | 0 | 0 | 0 | -9.4539 | -16.0068 | 4.5128 | -6.3295 | -27.2774 | Other Capex | 0% | 0% | 0% | 0% | -30.21% | -41.11% | 15.91% | -33.28% | -13.14%
of which IT | 14.7528 | 12.2964 | 9.1731 | 5.4313 | 2.4469 | 2.4469 | 6.2482 | 6.2482 | 59.0439 |  | of which IT | 0 | 0 | 0 | 0 | 1.1301 | 4.3788 | 4.6056 | -0.58918 | 9.5253 | of which IT | 0% | 0% | 0% | 0% | 46.18% | 178.9% | 73.71% | -9.43% | 16.13%
of which Vehicles | 2.1161 | 2.7337 | 2.4608 | 4.6255 | 7.2822 | 4.274 | 3.3671 | 2.5864 | 29.4458 |  | of which Vehicles | 0 | 0 | 0 | 0 | -0.57184 | 0.40152 | -1.3035 | 0.13191 | -1.3419 | of which Vehicles | 0% | 0% | 0% | 0% | -7.853% | 9.394% | -38.71% | 5.1% | -4.557%
Total Capex | 42.7907 | 49.4172 | 46.5105 | 47.0685 | 62.4875 | 72.0382 | 65.2197 | 53.2746 | 438.807 |  | Total Capex | 0 | 0 | 0 | 0 | -3.7049 | 9.3867 | 22.1658 | 10.2107 | 38.0583 | Total Capex | 0% | 0% | 0% | 0% | -5.929% | 13.03% | 33.99% | 19.17% | 8.673%
HSE driven mains & services | 95.1491 | 93.3655 | 94.0241 | 81.8174 | 88.0895 | 91.7186 | 91.7186 | 91.7186 | 727.6015 |  | HSE driven mains & services | 0 | 0 | 0 | 0 | -3.152 | 9.287 | 25.1696 | 5.4825 | 36.7872 | HSE driven mains & services | 0% | 0% | 0% | 0% | -3.578% | 10.13% | 27.44% | 5.978% | 5.056%
Non-HSE driven mains & services | 7.4131 | 14.7627 | 20.6235 | 18.8588 | 22.5447 | 16.063 | 15.4017 | 17.9467 | 133.6142 |  | Non-HSE driven mains & services | 0 | 0 | 0 | 0 | -1.3421 | 7.5438 | 13.0751 | 10.2432 | 29.52 | Non-HSE driven mains & services | 0% | 0% | 0% | 0% | -5.953% | 46.96% | 84.89% | 57.08% | 22.09%
Multi occupancy buildings (MoBs) | 0.61437 | 3.0914 | 2.0065 | 1.0872 | 1.9949 | 3.7873 | 3.8069 | 3.8703 | 20.2588 |  | Multi occupancy buildings (MoBs) | 0 | 0 | 0 | 0 | -0.64696 | -2.8227 | 0.44837 | 1.2268 | -1.7945 | Multi occupancy buildings (MoBs) | 0% | 0% | 0% | 0% | -32.43% | -74.53% | 11.78% | 31.7% | -8.858%
Total Repex | 103.1766 | 111.2196 | 116.6542 | 101.7634 | 112.6291 | 111.5688 | 110.9272 | 113.5356 | 881.4744 |  | Total Repex | 0 | 0 | 0 | 0 | -5.141 | 14.0081 | 38.693 | 16.9525 | 64.5127 | Total Repex | 0% | 0% | 0% | 0% | -4.565% | 12.56% | 34.88% | 14.93% | 7.319%
Work Management | 64.9407 | 37.4307 | 32.1199 | 31.9375 | 33.9995 | 32.8776 | 31.2148 | 30.6831 | 295.204 |  | Work Management | 0 | 0 | 0 | 0 | -4.1469 | -3.2855 | -2.2304 | -3.3272 | -12.99 | Work Management | 0% | 0% | 0% | 0% | -12.2% | -9.993% | -7.145% | -10.84% | -4.4%
Emergency | 17.5188 | 18.3817 | 16.8357 | 18.8283 | 16.602 | 16.5518 | 16.6832 | 16.342 | 137.7435 |  | Emergency | 0 | 0 | 0 | 0 | 2.1467 | 1.9275 | 0.79133 | 0.38661 | 5.2521 | Emergency | 0% | 0% | 0% | 0% | 12.93% | 11.65% | 4.743% | 2.366% | 3.813%
Repair | 16.2105 | 17.7161 | 16.9065 | 26.3649 | 18.0995 | 17.157 | 16.3925 | 15.9251 | 144.7721 |  | Repair | 0 | 0 | 0 | 0 | 4.3689 | 3.3914 | 3.4624 | 2.833 | 14.0557 | Repair | 0% | 0% | 0% | 0% | 24.14% | 19.77% | 21.12% | 17.79% | 9.709%
Maintenance | 24.6609 | 24.8435 | 28.8654 | 30.9629 | 31.2364 | 30.0227 | 29.9739 | 29.2674 | 229.8331 |  | Maintenance | 0 | 0 | 0 | 0 | -0.94051 | 1.0986 | 2.9874 | 0.95684 | 4.1023 | Maintenance | 0% | 0% | 0% | 0% | -3.011% | 3.659% | 9.967% | 3.269% | 1.785%
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory independent undertakings (SIUs) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Other Direct Activities | 10.4761 | 12.4832 | 10.7403 | 10.7366 | 9.5175 | 8.2807 | 8.2644 | 8.2687 | 78.7675 |  | Other Direct Activities | 0 | 0 | 0 | 0 | -0.37144 | 2.3849 | 1.7356 | 1.3512 | 5.1003 | Other Direct Activities | 0% | 0% | 0% | 0% | -3.903% | 28.8% | 21% | 16.34% | 6.475%
of which xoserve | 6.7293 | 7.4615 | 6.8915 | 5.9668 | 5.3137 | 4.2012 | 4.2012 | 4.2012 | 44.9665 |  | of which xoserve | 0 | 0 | 0 | 0 | -1.0455 | 2.7097 | 1.8692 | 1.4344 | 4.9677 | of which xoserve | 0% | 0% | 0% | 0% | -19.68% | 64.5% | 44.49% | 34.14% | 11.05%
Total Direct Opex | 133.8072 | 110.8552 | 105.4678 | 118.8302 | 109.4549 | 104.8899 | 102.5288 | 100.4862 | 886.3202 |  | Total Direct Opex | 0 | 0 | 0 | 0 | 1.0568 | 5.5168 | 6.7463 | 2.2005 | 15.5204 | Total Direct Opex | 0% | 0% | 0% | 0% | 0.9655% | 5.26% | 6.58% | 2.19% | 1.751%
Business support | 45.3593 | 45.3367 | 42.8745 | 41.6237 | 45.5894 | 44.052 | 40.0123 | 37.4187 | 342.2665 |  | Business support | 0 | 0 | 0 | 0 | -11.7733 | -12.7749 | -10.0374 | -9.1301 | -43.7157 | Business support | 0% | 0% | 0% | 0% | -25.82% | -29% | -25.09% | -24.4% | -12.77%
Training & Apprentices | 2.044 | 4.6494 | 6.7811 | 7.5022 | 7.8123 | 7.195 | 6.5302 | 6.0079 | 48.5223 |  | Training & Apprentices | 0 | 0 | 0 | 0 | 1.0562 | 2.3524 | 1.3404 | 1.3852 | 6.1342 | Training & Apprentices | 0% | 0% | 0% | 0% | 13.52% | 32.7% | 20.53% | 23.06% | 12.64%
Total Indirect Opex | 47.4033 | 49.9861 | 49.6556 | 49.1259 | 53.4018 | 51.247 | 46.5425 | 43.4266 | 390.7887 |  | Total Indirect Opex | 0 | 0 | 0 | 0 | -10.7171 | -10.4224 | -8.697 | -7.7449 | -37.5814 | Total Indirect Opex | 0% | 0% | 0% | 0% | -20.07% | -20.34% | -18.69% | -17.83% | -9.617%
Total Opex | 181.2104 | 160.8413 | 155.1235 | 167.9561 | 162.8567 | 156.1369 | 149.0713 | 143.9128 | 1277.1089 |  | Total Opex | 0 | 0 | 0 | 0 | -9.6603 | -4.9056 | -1.9507 | -5.5444 | -22.061 | Total Opex | 0% | 0% | 0% | 0% | -5.932% | -3.142% | -1.309% | -3.853% | -1.727%
Total sub-deducts | 0.091679 | 0.012369 | 0.015962 | 0.0043599 | 0 | 0 | 0 | 0 | 0 |  | Total sub-deducts | [9 empty] | Total sub-deducts | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Controllable costs | 327.1778 | 321.478 | 318.2881 | 316.788 | 337.9733 | 339.7439 | 325.2182 | 310.723 | 2597.3903 |  | Total Controllable costs | 0 | 0 | 0 | 0 | -18.5062 | 18.4892 | 58.9082 | 21.6188 | 80.51 | Total Controllable costs | 0% | 0% | 0% | 0% | -5.476% | 5.442% | 18.11% | 6.958% | 3.1%
Non-Controllable costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Non-Controllable costs | [9 empty] | Non-Controllable costs | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Licence/network/other | 72.523 | 77.1417 | 77.2446 | 77.4984 | 86.5346 | 84.4185 | 84.2479 | 84.307 | 643.9157 |  | Licence/network/other | 0 | 0 | 0 | 0 | -3.0952 | 0.65232 | -0.29191 | -1.2652 | -4 | Licence/network/other | 0% | 0% | 0% | 0% | -3.577% | 0.7727% | -0.3465% | -1.501% | -0.6212%
NTS exit costs | 29.2716 | 27.4711 | 24.549 | 25.7042 | 25.574 | 20.222 | 24.8677 | 22.721 | 200.3806 |  | NTS exit costs | 0 | 0 | 0 | 0 | -0.14765 | -0.91906 | -0.28948 | 3.4302 | 2.074 | NTS exit costs | 0% | 0% | 0% | 0% | -0.5774% | -4.545% | -1.164% | 15.1% | 1.035%
Shrinkage | 11.7063 | 8.7812 | 6.0157 | 5.9416 | 6.0016 | 6.005 | 6.0233 | 6.0432 | 56.5179 |  | Shrinkage | 0 | 0 | 0 | 0 | 0.69944 | 1.7043 | 0.028149 | -0.7203 | 1.7116 | Shrinkage | 0% | 0% | 0% | 0% | 11.65% | 28.38% | 0.4673% | -11.92% | 3.028%
NTS pensions contributions | 8.2221 | 8.3902 | 11.6398 | 11.4548 | 7.1018 | 7.1018 | 0 | 0 | 53.9106 |  | NTS pensions contributions | 0 | 0 | 0 | 0 | -0.00036582 | 0.0037716 | 0 | 0 | 0.0034057 | NTS pensions contributions | 0% | 0% | 0% | 0% | -0.005151% | 0.05311% | #DIV/0! | #DIV/0! | 0.006317%
Total non-controllable costs | 121.723 | 121.7842 | 119.4491 | 120.5991 | 125.2119 | 117.7473 | 115.1389 | 113.0712 | 954.7247 |  | Total non-controllable costs | 0 | 0 | 0 | 0 | -2.5438 | 1.4414 | -0.55324 | 1.4448 | -0.21092 | Total non-controllable costs | 0% | 0% | 0% | 0% | -2.032% | 1.224% | -0.4805% | 1.278% | -0.02209%
Total funded costs - including uncertainties | 448.9008 | 443.2622 | 437.7372 | 437.3871 | 463.1852 | 457.4912 | 440.3571 | 423.7942 | 3552.1151 |  | Total funded costs - including uncertainties | 0 | 0 | 0 | 0 | -21.05 | 19.9306 | 58.355 | 23.0636 | 80.2991 | Total funded costs - including uncertainties | 0% | 0% | 0% | 0% | -4.545% | 4.356% | 13.25% | 5.442% | 2.261%
Of which: uncertainties*: | [10 empty] | Of which: uncertainties*: | [9 empty] | Of which: uncertainties*:
Smart metering | 0.098504 | 0.18343 | 0.41747 | 0.89106 | 7.7325 | 9.8637 | 5.7511 | 5.8372 | 30.775 |  | Smart metering | 0 | 0 | 0 | 0 | -5.0474 | -5.7226 | 0.54461 | -1.9636 | -12.189 | Smart metering | 0 | 0 | 0 | 0 | -0.65275 | -0.58017 | 0.094696 | -0.33639 | -0.39607
Streetworks | 2.4025 | 5.8122 | 6.7726 | 5.5125 | 1.1647 | 1.1535 | 1.1422 | 1.1304 | 25.0907 |  | Streetworks | 0 | 0 | 0 | 0 | 5.4696 | 4.3276 | 6.9763 | 7.7563 | 24.5297 | Streetworks | 0 | 0 | 0 | 0 | 4.6962 | 3.7518 | 6.1078 | 6.8613 | 0.97764
Physical Security Upgrade Programme (PSUP) | -1.464 | 0.38692 | 0.3828 | 0.39737 | 5.9049 | 15.716 | 8.3751 | 0.56534 | 30.2644 |  | Physical Security Upgrade Programme (PSUP) | 0 | 0 | 0 | 0 | -2.4283 | -8.45 | 7.9574 | -0.56534 | -3.4863 | Physical Security Upgrade Programme (PSUP) | 0 | 0 | 0 | 0 | -0.41124 | -0.53767 | 0.95012 | -1 | -0.11519
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory independent undertakings (SIUs) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total uncertainties* | 1.037 | 6.3826 | 7.5729 | 6.801 | 14.802 | 26.7332 | 15.2684 | 7.533 | 86.1301 |  | Total uncertainties* | 0 | 0 | 0 | 0 | -2.0061 | -9.845 | 15.4783 | 5.2274 | 8.8545 | Total uncertainties* | 0 | 0 | 0 | 0 | -0.13553 | -0.36827 | 1.0137 | 0.69393 | 0.1028
Total funded costs - excluding uncertainties* | 447.8637 | 436.8796 | 430.1643 | 430.5861 | 448.3831 | 430.758 | 425.0887 | 416.2612 | 3465.985 |  | Total funded costs - excluding uncertainties* | 0 | 0 | 0 | 0 | -19.0439 | 29.7756 | 42.8767 | 17.8362 | 71.4446 | Total funded costs - excluding uncertainties* | 0 | 0 | 0 | 0 | -0.042472 | 0.069124 | 0.10087 | 0.042849 | 0.020613
Final proposals adjusted with agreed uncertainties - £m | [10 empty] | Variance from final proposals adjusted with uncertainties | [9 empty] | % Variance from final proposals adjusted with uncertainties
2017/18 prices
| Ofgem Allowance (Post IQI) £m | [10 empty] | Ofgem Allowance (Post IQI) £m | [9 empty] | Ofgem Allowance (Post IQI) £m
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
LTS, storage and entry | 13.1452 | 9.9449 | 9.7948 | 10.4463 | 7.3788 | 7.5377 | 7.3782 | 7.3623 | 72.9882 |  | LTS, storage and entry | -6.0866 | -0.29493 | -0.35308 | -1.8101 | 4.654 | 12.2745 | 18.2653 | 14.7028 | 41.3517 | LTS, storage and entry | -46.3% | -2.966% | -3.605% | -17.33% | 63.07% | 162.8% | 247.6% | 199.7% | 56.66%
Connections | 8.9501 | 9.0453 | 9.6463 | 9.8613 | 10.0883 | 10.1352 | 10.0966 | 10.0216 | 77.8448 |  | Connections | 1.618 | 2.6964 | 3.1711 | 4.6864 | 7.1938 | 7.3648 | 7.4034 | 7.4784 | 41.6122 | Connections | 18.08% | 29.81% | 32.87% | 47.52% | 71.31% | 72.66% | 73.33% | 74.62% | 53.46%
Mains Reinforcement | 4.6714 | 9.2434 | 6.4506 | 4.3915 | 4.4263 | 4.3595 | 4.1804 | 4.0537 | 41.7768 |  | Mains Reinforcement | -2.949 | -7.7808 | -4.6242 | -2.9005 | 2.0076 | 12.2324 | 0.21025 | 0.91412 | -2.8902 | Mains Reinforcement | -63.13% | -84.18% | -71.69% | -66.05% | 45.36% | 280.6% | 5.029% | 22.55% | -6.918%
Governors (Replacement) | 1.6272 | 2.0792 | 2.3298 | 2.7907 | 2.8917 | 3.0265 | 2.9043 | 3.1006 | 20.7501 |  | Governors (Replacement) | -0.5911 | -0.91544 | -1.2737 | -1.1215 | -1.693 | 1.5649 | 4.0618 | 3.1651 | 3.1971 | Governors (Replacement) | -36.33% | -44.03% | -54.67% | -40.19% | -58.55% | 51.71% | 139.9% | 102.1% | 15.41%
Other Capex | 37.2988 | 26.2749 | 20.9766 | 24.2673 | 42.3563 | 35.3078 | 20.3189 | 14.874 | 221.6746 |  | Other Capex | -14.8933 | -0.87582 | 0.39236 | -3.5428 | -20.5212 | -12.3783 | 12.5664 | -2.1874 | -41.44 | Other Capex | -39.93% | -3.333% | 1.87% | -14.6% | -48.45% | -35.06% | 61.85% | -14.71% | -18.69%
of which IT | 9.5527 | 6.4679 | 7.6466 | 6.434 | 22.2046 | 16.1338 | 5.9558 | 1.3987 | 75.7942 |  | of which IT | 5.2001 | 5.8285 | 1.5265 | -1.0027 | -18.6275 | -9.3081 | 4.898 | 4.2603 | -7.225 | of which IT | 54.44% | 90.11% | 19.96% | -15.58% | -83.89% | -57.69% | 82.24% | 304.6% | -9.532%
of which Vehicles | 7.4652 | 3.2792 | 2.1638 | 5.5587 | 5.797 | 5.818 | 3.5415 | 4.4102 | 38.0337 |  | of which Vehicles | -5.3491 | -0.54548 | 0.29697 | -0.9332 | 0.91332 | -1.1425 | -1.4779 | -1.6918 | -9.9298 | of which Vehicles | -71.65% | -16.63% | 13.72% | -16.79% | 15.75% | -19.64% | -41.73% | -38.36% | -26.11%
Total Capex | 65.6928 | 56.5878 | 49.198 | 51.7571 | 67.1413 | 60.3667 | 44.8785 | 39.4123 | 435.0345 |  | Total Capex | -22.902 | -7.1706 | -2.6876 | -4.6885 | -8.3588 | 21.0583 | 42.5071 | 24.073 | 41.8308 | Total Capex | -34.86% | -12.67% | -5.463% | -9.059% | -12.45% | 34.88% | 94.72% | 61.08% | 9.616%
HSE driven mains & services | -1.0677 | -0.97009 | -0.67114 | -1.1921 | 0 | 0 | 0 | 0 | -3.901 |  | HSE driven mains & services | 96.2168 | 94.3356 | 94.6953 | 83.0095 | 84.9376 | 101.0056 | 116.8882 | 97.2011 | 768.2897 | HSE driven mains & services | -9012% | -9724% | -14110% | -6963% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -19695%
Non-HSE driven mains & services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Non-HSE driven mains & services | 7.4131 | 14.7627 | 20.6235 | 18.8588 | 21.2026 | 23.6067 | 28.4768 | 28.1899 | 163.1342 | Non-HSE driven mains & services | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Multi occupancy buildings (MoBs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Multi occupancy buildings (MoBs) | 0.61437 | 3.0914 | 2.0065 | 1.0872 | 1.3479 | 0.96452 | 4.2553 | 5.0971 | 18.4643 | Multi occupancy buildings (MoBs) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Repex | 138.3251 | 135.8556 | 137.5298 | 137.1007 | 138.9487 | 139.5825 | 140.2371 | 140.8564 | 1108.4359 |  | Total Repex | -35.1485 | -24.636 | -20.8756 | -35.3373 | -31.4606 | -14.0056 | 9.3831 | -10.3682 | -162.4488 | Total Repex | -25.41% | -18.13% | -15.18% | -25.77% | -22.64% | -10.03% | 6.691% | -7.361% | -14.66%
Work Management | 35.335 | 32.2561 | 31.9271 | 31.7622 | 31.1473 | 30.5757 | 30.3457 | 31.208 | 254.5571 |  | Work Management | 29.6058 | 5.1746 | 0.19283 | 0.17532 | -1.2947 | -0.98356 | -1.3612 | -3.8521 | 27.6569 | Work Management | 83.79% | 16.04% | 0.604% | 0.552% | -4.157% | -3.217% | -4.486% | -12.34% | 10.86%
Emergency | 24.4191 | 24.2851 | 24.1794 | 24.1491 | 24.1404 | 24.0417 | 23.9589 | 23.9048 | 193.0784 |  | Emergency | -6.9003 | -5.9034 | -7.3437 | -5.3208 | -5.3916 | -5.5624 | -6.4844 | -7.1762 | -50.0827 | Emergency | -28.26% | -24.31% | -30.37% | -22.03% | -22.33% | -23.14% | -27.06% | -30.02% | -25.94%
Repair | 17.2398 | 16.8077 | 16.3504 | 15.8825 | 15.3986 | 14.8846 | 14.3406 | 13.7764 | 124.6806 |  | Repair | -1.0292 | 0.90837 | 0.55609 | 10.4824 | 7.0698 | 5.6637 | 5.5143 | 4.9817 | 34.1471 | Repair | -5.97% | 5.404% | 3.401% | 66% | 45.91% | 38.05% | 38.45% | 36.16% | 27.39%
Maintenance | 21.736 | 23.4207 | 24.9094 | 25.771 | 26.1063 | 26.1754 | 26.4662 | 26.0289 | 200.6138 |  | Maintenance | 2.9249 | 1.4228 | 3.956 | 5.1919 | 4.1896 | 4.9459 | 6.4952 | 4.1954 | 33.3216 | Maintenance | 13.46% | 6.075% | 15.88% | 20.15% | 16.05% | 18.9% | 24.54% | 16.12% | 16.61%
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory independent undertakings (SIUs) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Other Direct Activities | 14.1399 | 12.2789 | 13.6592 | 14.6163 | 9.6143 | 8.8025 | 7.9057 | 7.005 | 88.0218 |  | Other Direct Activities | -3.6637 | 0.20428 | -2.9189 | -3.8797 | -0.46825 | 1.8631 | 2.0943 | 2.6149 | -4.154 | Other Direct Activities | -25.91% | 1.664% | -21.37% | -26.54% | -4.87% | 21.17% | 26.49% | 37.33% | -4.719%
of which Xoserve | 8.6002 | 8.3671 | 9.6503 | 10.5608 | 5.6041 | 4.6916 | 3.6928 | 2.7212 | 53.888 |  | of which Xoserve | -1.8709 | -0.9056 | -2.7588 | -4.5939 | -1.3358 | 2.2193 | 2.3776 | 2.9144 | -3.9538 | of which Xoserve | -21.75% | -10.82% | -28.59% | -43.5% | -23.84% | 47.3% | 64.39% | 107.1% | -7.337%
Total Direct Opex | 112.8697 | 109.0484 | 111.0255 | 112.1811 | 106.4069 | 104.48 | 103.017 | 101.923 | 860.9518 |  | Total Direct Opex | 20.9375 | 1.8068 | -5.5577 | 6.6491 | 4.1048 | 5.9267 | 6.2581 | 0.76371 | 40.8889 | Total Direct Opex | 18.55% | 1.657% | -5.006% | 5.927% | 3.858% | 5.673% | 6.075% | 0.7493% | 4.749%
Business support | 31.1086 | 31.4727 | 31.4836 | 31.4191 | 31.5564 | 31.9509 | 32.16 | 32.383 | 253.5343 |  | Business support | 14.2507 | 13.8639 | 11.3909 | 10.2046 | 2.2598 | -0.67382 | -2.1852 | -4.0944 | 45.0165 | Business support | 45.81% | 44.05% | 36.18% | 32.48% | 7.161% | -2.109% | -6.795% | -12.64% | 17.76%
Training & Apprentices | 5.4253 | 6.3549 | 6.1242 | 6.3277 | 6.395 | 6.2498 | 5.9239 | 5.3644 | 48.1652 |  | Training & Apprentices | -3.3813 | -1.7055 | 0.65694 | 1.1745 | 2.4736 | 3.2976 | 1.9468 | 2.0287 | 6.4913 | Training & Apprentices | -62.32% | -26.84% | 10.73% | 18.56% | 38.68% | 52.76% | 32.86% | 37.82% | 13.48%
Total Indirect Opex | 36.5339 | 37.8277 | 37.6078 | 37.7468 | 37.9514 | 38.2008 | 38.0839 | 37.7474 | 301.6995 |  | Total Indirect Opex | 10.8694 | 12.1584 | 12.0478 | 11.3792 | 4.7333 | 2.6238 | -0.2384 | -2.0657 | 51.5078 | Total Indirect Opex | 29.75% | 32.14% | 32.04% | 30.15% | 12.47% | 6.868% | -0.626% | -5.472% | 17.07%
Total Opex | 149.6943 | 147.1667 | 148.9239 | 150.2185 | 144.6489 | 142.9714 | 141.3915 | 139.961 | 1164.9763 |  | Total Opex | 31.5162 | 13.6745 | 6.1995 | 17.7376 | 8.5475 | 8.2599 | 5.7291 | -1.5926 | 90.0716 | Total Opex | 21.05% | 9.292% | 4.163% | 11.81% | 5.909% | 5.777% | 4.052% | -1.138% | 7.732%
Total sub-deducts | 0.58127 | 0.58127 | 0.58127 | 0.58127 | 0.58127 | 0.58127 | 0.58127 | 0.58127 | 4.6502 |  | Total sub-deducts | -0.48959 | -0.5689 | -0.56531 | -0.57691 | -0.57692 | -0.58127 | -0.58127 | -0.58127 | -4.6502 | Total sub-deducts | -84.23% | -97.87% | -97.25% | -99.25% | -99.25% | -100% | -100% | -100% | -100%
Total Controllable costs | 353.7122 | 339.6102 | 335.6518 | 339.0763 | 350.739 | 342.9206 | 326.5071 | 320.2297 | 2708.4468 |  | Total Controllable costs | -26.5344 | -18.1321 | -17.3637 | -22.2882 | -31.272 | 15.3125 | 57.6193 | 12.1121 | -30.5464 | Total Controllable costs | -7.502% | -5.339% | -5.173% | -6.573% | -8.916% | 4.465% | 17.65% | 3.782% | -1.128%
Non-Controllable costs | [10 empty] | Non-Controllable costs | [9 empty] | Non-Controllable costs | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Licence/network/other | 66.9591 | 67.0586 | 67.0764 | 67.0764 | 67.0764 | 67.0764 | 67.0764 | 67.0764 | 536.4763 |  | Licence/network/other | 5.5639 | 10.083 | 10.1682 | 10.422 | 16.3629 | 17.9944 | 16.8796 | 15.9654 | 103.4393 | Licence/network/other | 8.309% | 15.04% | 15.16% | 15.54% | 24.39% | 26.83% | 25.16% | 23.8% | 19.28%
NTS exit costs | 31.5229 | 31.4958 | 31.4443 | 31.4443 | 31.4443 | 31.4443 | 31.4443 | 31.4443 | 251.6843 |  | NTS exit costs | -2.2513 | -4.0247 | -6.8953 | -5.74 | -6.0179 | -12.1413 | -6.8661 | -5.2931 | -49.2296 | NTS exit costs | -7.142% | -12.78% | -21.93% | -18.25% | -19.14% | -38.61% | -21.84% | -16.83% | -19.56%
Shrinkage | 15.2124 | 15.0206 | 14.9238 | 14.6407 | 14.4276 | 14.2122 | 13.9877 | 13.7209 | 116.1459 |  | Shrinkage | -3.5061 | -6.2394 | -8.9081 | -8.6991 | -7.7266 | -6.5029 | -7.9362 | -8.398 | -57.9163 | Shrinkage | -23.05% | -41.54% | -59.69% | -59.42% | -53.55% | -45.76% | -56.74% | -61.21% | -49.87%
NTS pensions contributions | 8.2444 | 8.2444 | 8.2444 | 8.2444 | 8.2444 | 8.2444 | 8.2444 | 8.2444 | 65.955 |  | NTS pensions contributions | -0.022247 | 0.14582 | 3.3954 | 3.2104 | -1.1429 | -1.1388 | -8.2444 | -8.2444 | -12.041 | NTS pensions contributions | -0.2698% | 1.769% | 41.18% | 38.94% | -13.86% | -13.81% | -100% | -100% | -18.26%
Total non-controllable costs | 121.9388 | 121.8194 | 121.6888 | 121.4058 | 121.1926 | 120.9773 | 120.7527 | 120.486 | 970.2615 |  | Total non-controllable costs | -0.21577 | -0.035211 | -2.2397 | -0.8067 | 1.4755 | -1.7886 | -6.1671 | -5.9701 | -15.7476 | Total non-controllable costs | -0.177% | -0.0289% | -1.841% | -0.6645% | 1.217% | -1.478% | -5.107% | -4.955% | -1.623%
Total funded costs - including agreed uncertainties** | 475.651 | 461.4295 | 457.3406 | 460.482 | 471.9316 | 463.8979 | 447.2599 | 440.7157 | 3678.7082 |  | Total funded costs - including uncertainties | -26.7502 | -18.1673 | -19.6034 | -23.0949 | -29.7965 | 13.5239 | 51.4522 | 6.1421 | -46.2941 | Total funded costs - including uncertainties | -5.624% | -3.937% | -4.286% | -5.015% | -6.314% | 2.915% | 11.5% | 1.394% | -1.258%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | -0.74467
Final proposals - £m
2009/10 prices
Ofgem Allowance (Post IQI) £m
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
LTS, storage and entry | 10.3173 | 7.8055 | 7.6876 | 8.199 | 5.7914 | 5.9161 | 5.7909 | 5.7784 | 57.2862
Connections | 7.0247 | 7.0994 | 7.2207 | 7.3894 | 7.5676 | 7.6044 | 7.5741 | 7.5152 | 58.9955
Mains Reinforcement | 3.6665 | 7.2549 | 5.0629 | 3.4467 | 3.474 | 3.4216 | 3.2811 | 3.1816 | 32.7893
Governors (Replacement) | 1.2771 | 1.6319 | 1.8286 | 2.1904 | 2.2696 | 2.3754 | 2.2795 | 2.4336 | 16.2861
Other Capex | 30.5505 | 20.4831 | 16.1379 | 16.8235 | 20.975 | 18.6161 | 14.8976 | 12.5443 | 151.028
of which IT | 8.7734 | 4.9372 | 5.6756 | 2.8267 | 5.1586 | 3.567 | 3.6244 | 1.968 | 36.531
of which Vehicles | 5.8592 | 2.5737 | 1.6983 | 4.3629 | 4.5499 | 4.5664 | 2.7796 | 3.4614 | 29.8514
Total Capex | 52.836 | 44.2748 | 37.9376 | 38.0489 | 40.0776 | 37.9336 | 33.8232 | 31.4532 | 316.3851
HSE driven mains & services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-HSE driven mains & services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Multi occupancy buildings (MoBs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Repex | 109.4051 | 107.3902 | 108.4696 | 108.5417 | 109.0565 | 109.5539 | 110.0677 | 110.5538 | 873.0385
Work Management | 27.7333 | 25.3168 | 25.0586 | 24.9292 | 24.4466 | 23.9979 | 23.8174 | 24.4942 | 199.7939
Emergency | 19.1658 | 19.0606 | 18.9776 | 18.9539 | 18.947 | 18.8696 | 18.8046 | 18.7621 | 151.5412
Repair | 13.531 | 13.1919 | 12.8329 | 12.4657 | 12.0859 | 11.6825 | 11.2555 | 10.8126 | 97.8579
Maintenance | 16.9933 | 18.3061 | 19.4279 | 20.0863 | 20.3519 | 20.314 | 20.3691 | 19.9673 | 155.8158
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Activities | 11.0979 | 9.6193 | 10.5464 | 11.2951 | 9.7965 | 10.2636 | 10.6196 | 10.4512 | 83.6896
of which Xoserve | 6.75 | 6.549 | 7.4 | 8.112 | 6.649 | 7.037 | 7.313 | 7.089 | 56.899
Total Direct Opex | 88.5213 | 85.4946 | 86.8435 | 87.7301 | 85.6279 | 85.1276 | 84.8661 | 84.4874 | 688.6984
Business support | 24.4161 | 24.702 | 24.7105 | 24.6599 | 24.7676 | 25.0773 | 25.2414 | 25.4164 | 198.9911
Training & Apprentices | 4.2582 | 4.9878 | 4.8067 | 4.9664 | 5.0192 | 4.9053 | 4.6495 | 4.2103 | 37.8034
Total Indirect Opex | 28.6743 | 29.6898 | 29.5172 | 29.6263 | 29.7868 | 29.9826 | 29.8908 | 29.6267 | 236.7945
Total Opex | 117.4237 | 115.4125 | 116.5887 | 117.5845 | 115.6428 | 115.3382 | 114.9851 | 114.3423 | 927.3178
Total sub-deducts | 0.45622 | 0.45622 | 0.45622 | 0.45622 | 0.45622 | 0.45622 | 0.45622 | 0.45622 | 3.6498
Total Controllable costs | 279.6648 | 267.0774 | 262.996 | 264.1751 | 264.777 | 262.8258 | 258.8761 | 256.3493 | 2116.7414
Non-Controllable costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Licence/network/other | 52.5541 | 52.6322 | 52.6462 | 52.6462 | 52.6462 | 52.6462 | 52.6462 | 52.6462 | 421.0635
NTS exit costs | 24.7413 | 24.7201 | 24.6796 | 24.6796 | 24.6796 | 24.6796 | 24.6796 | 24.6796 | 197.5391
Shrinkage | 11.9398 | 11.7892 | 11.7132 | 11.491 | 11.3237 | 11.1547 | 10.9785 | 10.7691 | 91.1593
NTS pensions contributions | 6.4707 | 6.4707 | 6.4707 | 6.4707 | 6.4707 | 6.4707 | 6.4707 | 6.4707 | 51.766
Total non-controllable costs | 95.7059 | 95.6122 | 95.5098 | 95.2876 | 95.1203 | 94.9513 | 94.7751 | 94.5657 | 761.5279
Total funded costs | 375.3708 | 362.6897 | 358.5057 | 359.4627 | 359.8973 | 357.7771 | 353.6511 | 350.915 | 2878.2693
Agreed Uncertainties** £m | [8 empty] | ok
2009-10 prices
Ofgem Allowance (Post IQI) £m
Uncertainty | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
Smart metering | [8 empty] | 0
Streetworks | [8 empty] | 0
PSUP | -1.2092 | 0.21213 | 0.41797 | 2.3325 | 12.8044 | 9.9182 | 2.2325 | 0.46585 | 27.1744
SIUs | [8 empty] | 0
Other - fuel poor | 0 | 0 | 0.35041 | 0.35041 | 0.35041 | 0.35041 | 0.35041 | 0.35041 | 2.1024
Tier 2A adjustment | -0.83801 | -0.7614 | -0.52676 | -0.93563 |  |  |  |  | -3.0618
Central Agent (FGO) | -8.5304e-07 | 0.021238 | 0.20501 | 0.208 | -2.6477 | -3.9468 | -5.1937 | -5.8273 | -17.1812
London Medium Pressure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | -2.0472 | -0.52802 | 0.44663 | 1.9553 | 10.5071 | 6.3218 | -2.6108 | -5.011 | 9.0338
[9 empty] | 0 | check
Agreed uncertainties** by activity £m
Ofgem Allowance (Post IQI) £m
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
LTS, storage and entry | [8 empty] | 0
Connections | 0 | 0 | 0.35041 | 0.35041 | 0.35041 | 0.35041 | 0.35041 | 0.35041 | 2.1024
Mains Reinforcement | [8 empty] | 0
Governors (Replacement) | [8 empty] | 0
Other Capex | -1.2758 | 0.13924 | 0.32598 | 2.2231 | 12.2691 | 9.0959 | 1.0501 | -0.87018 | 22.9574
of which IT | -1.2758 | 0.13924 | 0.32598 | 2.2231 | 12.2691 | 9.0959 | 1.0501 | -0.87018 | 22.9574
of which Vehicles | [8 empty] | 0
Total Capex | -1.2758 | 0.13924 | 0.67639 | 2.5736 | 12.6195 | 9.4463 | 1.4005 | -0.51977 | 25.0599
HSE driven mains & services | -0.83801 | -0.7614 | -0.52676 | -0.93563 | 0 | 0 | 0 | 0 | -3.0618
Non-HSE driven mains & services | [8 empty] | 0
Multi occupancy buildings (MoBs) | [8 empty] | 0
Total Repex | -0.83801 | -0.7614 | -0.52676 | -0.93563 | 0 | 0 | 0 | 0 | -3.0618
Work Management | [8 empty] | 0
Emergency | [8 empty] | 0
Repair | [8 empty] | 0
Maintenance | 0.066611 | 0.076077 | 0.12275 | 0.14055 | 0.13816 | 0.23028 | 0.40337 | 0.46194 | 1.6397
Statutory independent undertakings (SIUs) | [8 empty] | 0
Other Direct Activities | -7.2508e-07 | 0.018053 | 0.17426 | 0.1768 | -2.2505 | -3.3547 | -4.4147 | -4.9532 | -14.604
of which Xoserve | -7.2508e-07 | 0.018053 | 0.17426 | 0.1768 | -2.2505 | -3.3547 | -4.4147 | -4.9532 | -14.604
Total Direct Opex | 0.06661 | 0.09413 | 0.297 | 0.31735 | -2.1124 | -3.1245 | -4.0113 | -4.4913 | -12.9643
Business support | [8 empty] | 0
Training & Apprentices | [8 empty] | 0
Total Indirect Opex | [8 empty] | 0
Total Opex | 0.06661 | 0.09413 | 0.297 | 0.31735 | -2.1124 | -3.1245 | -4.0113 | -4.4913 | -12.9643
Total Controllable costs | -2.0472 | -0.52802 | 0.44663 | 1.9553 | 10.5071 | 6.3218 | -2.6108 | -5.011 | 9.0338
0
| OK | OK | OK | OK | OK | OK | OK | OK | OK
* These are uncertainties where a reopener has yet to be triggered and no decision on setting an allowance has been made.
** Agreed uncertainties are where a reopener has been triggered and a decision has been made by Ofgem.

## 2.3 Workload summary
Regulatory Reporting Pack
Cadent East of England
2017/18
2.3 Summary of workload
Current year RRP submission 2018 - Workload
|  | Actuals |  |  |  | Current year actuals | Forecast |  |  | Forecast RIIO Total
Cost activity |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Opex
Mains condition reports | Number | 5099.1 | 6969.9 | 6189.8 | 7453.25 | 6415.96 | 6288 | 6163 | 6039 | 50618.01
Service condition reports | Number | 14734.52 | 15261.15 | 15711.49 | 15776.39 | 15258.6 | 14954 | 14655 | 14361 | 120712.15
No. of holders removed | Number | 9 | 5 | 9 | 5 | 4 | 8 | 12 | 8 | 60
Capex
Total mains reinforcement | km | 4.4668 | 7.2888 | 6.0239 | 14.4434 | 10.619 | 29 | 20 | 22 | 113.8419
Total reinforcement Governors | Number | 0 | 1 | 3 | 2 | 0 | 2 | 2 | 2 | 12
Total connection services | Number | 8514 | 8392 | 9077 | 9071 | 9221 | 9260 | 9433 | 9559 | 72527
- New housing services | Number | 2005 | 2746 | 2671 | 3044 | 3366 | 2790 | 2878 | 2912 | 22412
- Existing housing services | Number | 4748 | 4206 | 4734 | 4212 | 3712 | 4771 | 4922 | 4980 | 36285
- Non- domestic services | Number | 136 | 135 | 188 | 262 | 222 | 249 | 279 | 313 | 1784
- Fuel poor services | Number | 1625 | 1305 | 1484 | 1553 | 1921 | 1450 | 1354 | 1354 | 12046
Governor intervention | Number | 17 | 8 | 9 | 36 | 64 | 55 | 62 | 60 | 311
Repex
T1 length decommissioned | km | 561.1418 | 557.9246 | 615.5855 | 529.4147 | 495.3084 | 604 | 663.1 | 555.1 | 4581.575
T2 length decommissioned | km | 2.8815 | 4.872 | 12.4931 | 8.5666 | 11.3262 | 19 | 22.6 | 22.6 | 104.3394
T3 length decommissioned | km | 0.279 | 1.7635 | 1.0771 | 1.4357 | 4.4058 | 5 | 4.5 | 4.5 | 22.9611
Steel length decommissioned | km | 5.9178 | 14.6703 | 24.0215 | 16.7793 | 29.1591 | 32.6 | 47.9 | 47.9 | 218.948
Other length decommissioned | km | 7.1808 | 7.2542 | 8.1103 | 15.5596 | 0 | 26.7 | 28.4 | 28.4 | 121.6048
No. of services transferred | Number | 26354 | 26035 | 28487 | 23735 | 25163 | 29660 | 33073 | 28413 | 220920
No. of services relaid | Number | 33943.9 | 35960.27 | 32123.9213 | 29823.5978 | 27263.9518 | 32807 | 35988 | 31646 | 259556.6409
Previous year RRP submission | [10 empty] | Variance from previous year | [10 empty] | % Variance from previous year
|  | 2014: Actuals; 2018: Previous year forecast |  |  |  | Actuals |  |  | Current year actuals | Forecast | [6 empty] | Actuals |  |  | Current year actuals | Forecast
Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Opex | [10 empty] | Opex | [10 empty] | Opex
Mains condition reports | Number | 5099.1 | 6969.9 | 6189.8 | 7453.25 | 6611 | 6479 | 6349 | 6222 | 51373.05 | Mains condition reports | Number | 0 | 0 | 0 | 0 | -195.04 | -191 | -186 | -183 | -755.04 | Mains condition reports | Number | 0% | 0% | 0% | 0% | -2.95% | -2.948% | -2.93% | -2.941% | -1.47%
Service condition reports | Number | 14734.52 | 15261.15 | 15711.49 | 15776.39 | 15733 | 15418 | 15110 | 14808 | 122552.55 | Service condition reports | Number | 0 | 0 | 0 | 0 | -474.4 | -464 | -455 | -447 | -1840.4 | Service condition reports | Number | 0% | 0% | 0% | 0% | -3.015% | -3.009% | -3.011% | -3.019% | -1.502%
No. of holders removed | Number | 9 | 5 | 9 | 5 | 0 | 0 | 0 | 1 | 29 | No. of holders removed | Number | 0 | 0 | 0 | 0 | 4 | 8 | 12 | 7 | 31 | No. of holders removed | Number | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | 700% | 106.9%
Capex | [10 empty] | Capex | [10 empty] | Capex
Total mains reinforcement | km | 4.4668 | 7.2888 | 6.0239 | 14.4434 | 11.75 | 15 | 15 | 20 | 93.9729 | Total mains reinforcement | km | 0 | 0 | 0 | 0 | -1.131 | 14 | 5 | 2 | 19.869 | Total mains reinforcement | km | 0% | 0% | 0% | 0% | -9.626% | 93.33% | 33.33% | 10% | 21.14%
Total reinforcement Governors | Number | 0 | 1 | 3 | 2 | 2 | 2 | 2 | 2 | 14 | Total reinforcement Governors | Number | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | -2 | Total reinforcement Governors | Number | #DIV/0! | 0% | 0% | 0% | -100% | 0% | 0% | 0% | -14.29%
Total connection services | Number | 8514 | 8392 | 9077 | 9071 | 9199 | 9317 | 9447 | 9583 | 72600 | Total connection services | Number | 0 | 0 | 0 | 0 | 22 | -57 | -14 | -24 | -73 | Total connection services | Number | 0% | 0% | 0% | 0% | 0.2392% | -0.6118% | -0.1482% | -0.2504% | -0.1006%
- New housing services | Number | 2005 | 2746 | 2671 | 3044 | 2709.2942 | 2741.7629 | 2774.9695 | 2808.5452 | 21500.5717 | - New housing services | Number | 0 | 0 | 0 | 0 | 656.7058 | 48.2371 | 103.0305 | 103.4548 | 911.4283 | - New housing services | Number | 0% | 0% | 0% | 0% | 24.24% | 1.759% | 3.713% | 3.684% | 4.239%
- Existing housing services | Number | 4748 | 4206 | 4734 | 4212 | 4633.7058 | 4689.2371 | 4746.0305 | 4803.4548 | 36772.4283 | - Existing housing services | Number | 0 | 0 | 0 | 0 | -921.7058 | 81.7629 | 175.9695 | 176.5452 | -487.4283 | - Existing housing services | Number | 0% | 0% | 0% | 0% | -19.89% | 1.744% | 3.708% | 3.675% | -1.326%
- Non- domestic services | Number | 136 | 135 | 188 | 262 | 294 | 329 | 369 | 414 | 2127 | - Non- domestic services | Number | 0 | 0 | 0 | 0 | -72 | -80 | -90 | -101 | -343 | - Non- domestic services | Number | 0% | 0% | 0% | 0% | -24.49% | -24.32% | -24.39% | -24.4% | -16.13%
- Fuel poor services | Number | 1625 | 1305 | 1484 | 1553 | 1562 | 1557 | 1557 | 1557 | 12200 | - Fuel poor services | Number | 0 | 0 | 0 | 0 | 359 | -107 | -203 | -203 | -154 | - Fuel poor services | Number | 0% | 0% | 0% | 0% | 22.98% | -6.872% | -13.04% | -13.04% | -1.262%
Governor intervention | Number | 17 | 8 | 9 | 36 | 107 | 106 | 106 | 106 | 495 | Governor intervention | Number | 0 | 0 | 0 | 0 | -43 | -51 | -44 | -46 | -184 | Governor intervention | Number | 0% | 0% | 0% | 0% | -40.19% | -48.11% | -41.51% | -43.4% | -37.17%
Repex | [10 empty] | Repex | [10 empty] | Repex
T1 length decommissioned | km | 561.1418 | 557.9246 | 615.5855 | 529.4147 | 570 | 593.4825 | 593.4825 | 593.4825 | 4614.5141 | T1 length decommissioned | km | 0 | 0 | 0 | 0 | -74.6916 | 10.5175 | 69.6175 | -38.3825 | -32.9391 | T1 length decommissioned | km | 0% | 0% | 0% | 0% | -13.1% | 1.772% | 11.73% | -6.467% | -0.7138%
T2 length decommissioned | km | 2.8815 | 4.872 | 12.4931 | 8.5666 | 12.829 | 19.5883 | 19.5883 | 19.5883 | 100.4071 | T2 length decommissioned | km | 0 | 0 | 0 | 0 | -1.5028 | -0.58829 | 3.0117 | 3.0117 | 3.9323 | T2 length decommissioned | km | 0% | 0% | 0% | 0% | -11.71% | -3.003% | 15.38% | 15.38% | 3.916%
T3 length decommissioned | km | 0.279 | 1.7635 | 1.0771 | 1.4357 | 2.952 | 8.8661 | 8.8661 | 8.8661 | 34.1055 | T3 length decommissioned | km | 0 | 0 | 0 | 0 | 1.4538 | -3.8661 | -4.3661 | -4.3661 | -11.1444 | T3 length decommissioned | km | 0% | 0% | 0% | 0% | 49.25% | -43.61% | -49.24% | -49.24% | -32.68%
Steel length decommissioned | km | 5.9178 | 14.6703 | 24.0215 | 16.7793 | 20 | 41.737 | 41.737 | 41.737 | 206.6 | Steel length decommissioned | km | 0 | 0 | 0 | 0 | 9.1591 | -9.137 | 6.163 | 6.163 | 12.348 | Steel length decommissioned | km | 0% | 0% | 0% | 0% | 45.8% | -21.89% | 14.77% | 14.77% | 5.977%
Other length decommissioned | km | 7.1808 | 7.2542 | 8.1103 | 15.5596 | 8 | 9.6483 | 9.6483 | 9.6483 | 75.0496 | Other length decommissioned | km | 0 | 0 | 0 | 0 | -8 | 17.0517 | 18.7517 | 18.7517 | 46.5552 | Other length decommissioned | km | 0% | 0% | 0% | 0% | -100% | 176.7% | 194.4% | 194.4% | 62.03%
No. of services transferred | Number | 26354 | 26035 | 28487 | 23735 | 26787.7136 | 29386.3135 | 29386.3135 | 29386.3135 | 219557.6543 | No. of services transferred | Number | 0 | 0 | 0 | 0 | -1624.7136 | 273.6865 | 3686.6865 | -973.3135 | 1362.3457 | No. of services transferred | Number | 0% | 0% | 0% | 0% | -6.065% | 0.9313% | 12.55% | -3.312% | 0.6205%
No. of services relaid | Number | 33943.9 | 35960.27 | 32123.9213 | 29823.5978 | 34478.5362 | 37823.2009 | 37823.2009 | 37823.2009 | 279799.8281 | No. of services relaid | Number | 0 | 0 | 0 | 0 | -7214.5844 | -5016.2009 | -1835.2009 | -6177.2009 | -20243.1872 | No. of services relaid | Number | 0% | 0% | 0% | 0% | -20.92% | -13.26% | -4.852% | -16.33% | -7.235%
Final proposals | [10 empty] | Variance from final proposals | [10 empty] | % Variance from final proposals
[13 empty] | Actuals |  |  | Current year actuals | Forecast | [6 empty] | Actuals |  |  | Current year actuals | Forecast
Workload
Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
Opex | [10 empty] | Opex | [10 empty] | Opex
Mains condition reports | Number | 9112.3013 | 8880.8819 | 8654.1353 | 8434.9609 | 8223.2765 | 8018.8785 | 7821.6312 | 7631.4044 | 66777.47 | Mains condition reports | Number | -4013.2013 | -1910.9819 | -2464.3353 | -981.7109 | -1807.3165 | -1730.8785 | -1658.6312 | -1592.4044 | -16159.46 | Mains condition reports | Number | -44.04% | -21.52% | -28.48% | -11.64% | -21.98% | -21.59% | -21.21% | -20.87% | -24.2%
Service condition reports | Number | 9936.3761 | 9670.2376 | 9373.7509 | 9049.5977 | 8696.519 | 8313.0498 | 7897.7801 | 7449.2612 | 70386.5723 | Service condition reports | Number | 4798.1439 | 5590.9124 | 6337.7391 | 6726.7923 | 6562.081 | 6640.9502 | 6757.2199 | 6911.7388 | 50325.5777 | Service condition reports | Number | 48.29% | 57.82% | 67.61% | 74.33% | 75.46% | 79.89% | 85.56% | 92.78% | 71.5%
No. of holders removed | Number | c. 3-4 | c. 3-4 | c. 3-4 | c. 3-4 | c. 3-4 | c. 3-4 | c. 3-4 | c. 3-4 | c. 29-30 | No. of holders removed | Number | [9 empty] | No. of holders removed | Number | [8 empty] | #VALUE!
Capex | [10 empty] | Capex | [10 empty] | Capex
Total mains reinforcement | km | 9.86 | 23.4 | 14.9 | 10.3 | 11.68 | 12.03 | 11.2 | 11.08 | 104.45 | Total mains reinforcement | km | -5.3932 | -16.1112 | -8.8761 | 4.1434 | -1.061 | 16.97 | 8.8 | 10.92 | 9.3919 | Total mains reinforcement | km | -54.7% | -68.85% | -59.57% | 40.23% | -9.084% | 141.1% | 78.57% | 98.56% | 8.992%
Total reinforcement Governors | Number | 22 | 8 | 6 | 6 | 5 | 4 | 4 | 4 | 59 | Total reinforcement Governors | Number | -22 | -7 | -3 | -4 | -5 | -2 | -2 | -2 | -47 | Total reinforcement Governors | Number | -100% | -87.5% | -50% | -66.67% | -100% | -50% | -50% | -50% | -79.66%
Total connection services | Number | 8903.593 | 9038.2085 | 9238.4652 | 9441.2038 | 9648.052 | 9683.613 | 9683.613 | 9583.613 | 75220.3616 | Total connection services | Number | -389.593 | -646.2085 | -161.4652 | -370.2038 | -427.052 | -423.613 | -250.613 | -24.613 | -2693.3616 | Total connection services | Number | -4.376% | -7.15% | -1.748% | -3.921% | -4.426% | -4.375% | -2.588% | -0.2568% | -3.581%
- New housing services | Number | 2243.593 | 2378.2085 | 2568.4652 | 2671.2038 | 2778.052 | 2833.613 | 2833.613 | 2833.613 | 21140.3616 | - New housing services | Number | -238.593 | 367.7915 | 102.5348 | 372.7962 | 587.948 | -43.613 | 44.387 | 78.387 | 1271.6384 | - New housing services | Number | -10.63% | 15.47% | 3.992% | 13.96% | 21.16% | -1.539% | 1.566% | 2.766% | 6.015%
- Existing housing services | Number | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 44000 | - Existing housing services | Number | -752 | -1294 | -766 | -1288 | -1788 | -729 | -578 | -520 | -7715 | - Existing housing services | Number | -13.67% | -23.53% | -13.93% | -23.42% | -32.51% | -13.25% | -10.51% | -9.455% | -17.53%
- Non- domestic services | Number | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - Non- domestic services | Number | 136 | 135 | 188 | 262 | 222 | 249 | 279 | 313 | 1784 | - Non- domestic services | Number | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
- Fuel poor services | Number | 1160 | 1160 | 1170 | 1270 | 1370 | 1350 | 1350 | 1250 | 10080 | - Fuel poor services | Number | 465 | 145 | 314 | 283 | 551 | 100 | 4 | 104 | 1966 | - Fuel poor services | Number | 40.09% | 12.5% | 26.84% | 22.28% | 40.22% | 7.407% | 0.2963% | 8.32% | 19.5%
Governor intervention | Number | 17 | 21 | 23 | 27 | 28 | 29 | 28 | 29 | 202 | Governor intervention | Number | 0 | -13 | -14 | 9 | 36 | 26 | 34 | 31 | 109 | Governor intervention | Number | 0% | -61.9% | -60.87% | 33.33% | 128.6% | 89.66% | 121.4% | 106.9% | 53.96%
Repex | [10 empty] | Repex | [10 empty] | Repex
T1 length decommissioned | km | 585.7463 | 584.3331 | 583.5645 | 582.7069 | 581.998 | 581.3167 | 580.662 | 580.0329 | 4660.3604 | T1 length decommissioned | km | -24.6045 | -26.4085 | 32.021 | -53.2921 | -86.6896 | 22.6833 | 82.438 | -24.9329 | -78.7854 | T1 length decommissioned | km | -4.201% | -4.519% | 5.487% | -9.146% | -14.9% | 3.902% | 14.2% | -4.299% | -1.691%
T2 length decommissioned | km | 13.3937 | 13.3833 | 13.3834 | 13.3814 | 13.3815 | 13.3816 | 13.3817 | 13.3818 | 107.0685 | T2 length decommissioned | km | -10.5122 | -8.5113 | -0.89029 | -4.8148 | -2.0553 | 5.6184 | 9.2183 | 9.2182 | -2.7291 | T2 length decommissioned | km | -78.49% | -63.6% | -6.652% | -35.98% | -15.36% | 41.99% | 68.89% | 68.89% | -2.549%
T3 length decommissioned | km | 7.4787 | 3.7341 | 3.7341 | 3.7334 | 3.7335 | 3.7335 | 3.7335 | 3.7336 | 33.6144 | T3 length decommissioned | km | -7.1997 | -1.9706 | -2.657 | -2.2977 | 0.67235 | 1.2665 | 0.76648 | 0.76644 | -10.6533 | T3 length decommissioned | km | -96.27% | -52.77% | -71.16% | -61.54% | 18.01% | 33.92% | 20.53% | 20.53% | -31.69%
Steel length decommissioned | km | 22.9243 | 22.3455 | 22.4455 | 21.7043 | 21.6849 | 21.6685 | 21.6527 | 21.6376 | 176.0633 | Steel length decommissioned | km | -17.0065 | -7.6752 | 1.576 | -4.925 | 7.4742 | 10.9315 | 26.2473 | 26.2624 | 42.8847 | Steel length decommissioned | km | -74.19% | -34.35% | 7.022% | -22.69% | 34.47% | 50.45% | 121.2% | 121.4% | 24.36%
Other length decommissioned | km | 8.656 | 8.6473 | 8.6474 | 8.6458 | 8.6458 | 8.6459 | 8.646 | 8.6461 | 69.1804 | Other length decommissioned | km | -1.4752 | -1.3931 | -0.53714 | 6.9138 | -8.6458 | 18.0541 | 19.754 | 19.7539 | 52.4245 | Other length decommissioned | km | -17.04% | -16.11% | -6.212% | 79.97% | -100% | 208.8% | 228.5% | 228.5% | 75.78%
No. of services transferred | Number | 27175.5778 | 27098.0484 | 27068.3054 | 27013.3933 | 26980.978 | 26949.9234 | 26920.0799 | 26891.4003 | 216097.7065 | No. of services transferred | Number | -821.5778 | -1063.0484 | 1418.6946 | -3278.3933 | -1817.978 | 2710.0766 | 6152.9201 | 1521.5997 | 4822.2935 | No. of services transferred | Number | -3.023% | -3.923% | 5.241% | -12.14% | -6.738% | 10.06% | 22.86% | 5.658% | 2.232%
No. of services relaid | Number | 31426.4622 | 31201.5478 | 31009.9555 | 30781.3622 | 30560.7042 | 30324.4427 | 30073.691 | 29807.7738 | 245185.9395 | No. of services relaid | Number | 2517.4378 | 4758.7222 | 1113.9659 | -957.7644 | -3296.7524 | 2482.5573 | 5914.309 | 1838.2262 | 14370.7015 | No. of services relaid | Number | 8.011% | 15.25% | 3.592% | -3.112% | -10.79% | 8.187% | 19.67% | 6.167% | 5.861%

## 2.4 Safety
Regulatory Reporting Pack
Cadent East of England
2017/18
2.4 Summary of safety outputs and secondary deliverables
Actual/forecast iron mains risk reduction (incidents/year x 10-6) - Primary output
| Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Mains risk b/f | 432076 | 388279 | 352720 | 317807.12 | 289217.0492 | 265444.0492 | 236799.0492 | 214083.0492
Mains risk reduction | 43797 | 35559 | 34912.88 | 28590.0708 | 23773 | 28645 | 22716 | 22716
Main risk c/f | 388279 | 352720 | 317807.12 | 289217.0492 | 265444.0492 | 236799.0492 | 214083.0492 | 191367.0492
Cumulative mains risk reduction | 43797 | 79356 | 114268.88 | 142858.9508 | 166631.9508 | 195276.9508 | 217992.9508 | 240708.9508
Previous year forecast iron mains risk reduction (incidents/year x 10-6) | [8 empty] | Variance from previous year | [8 empty] | % Variance from previous year
| Actuals |  |  |  | Current year actuals | Forecast |  |  |  | Actuals | Forecast | [7 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Mains risk b/f | 432076 | 388279 | 352720 | 317807.12 | 289217.0492 | 261384.0492 | 246389.6862 | 231395.3231
Mains risk reduction | 43797 | 35559 | 34912.88 | 28590.0708 | 27833 | 14994.3631 | 14994.3631 | 14994.3631 | Mains risk reduction | 0 | 0 | 0 | 0 | -4060 | 13650.6369 | 7721.6369 | 7721.6369 | Mains risk reduction | 0% | 0% | 0% | 0% | -14.59% | 91.04% | 51.5% | 51.5%
Main risk c/f | 388279 | 352720 | 317807.12 | 289217.0492 | 261384.0492 | 246389.6862 | 231395.3231 | 216400.96
Cumulative mains risk reduction | 43797 | 79356 | 114268.88 | 142858.9508 | 170691.9508 | 185686.3138 | 200680.6769 | 215675.04 | Cumulative mains risk reduction | 0 | 0 | 0 | 0 | -4060 | 9590.6369 | 17312.2738 | 25033.9108 | Cumulative mains risk reduction | 0% | 0% | 0% | 0% | -2.379% | 5.165% | 8.627% | 11.61%
Final proposals allowed iron mains risk reduction for RIIO-GD1 (incidents/year x 10-6) | [8 empty] | Variance from final proposals | [8 empty] | % Variance from final proposals
| Final proposals | [8 empty] | Final proposals | [8 empty] | Final proposals
Mains risk reduction | 192567 | [7 empty] | Mains risk reduction | 48141.9508 | [7 empty] | Mains risk reduction | -100%
Actual/forecast repair risk (x106)
| Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Repair risk 2013 (start position) | 5166275
Annual repair risk | 3023211 | 4994106 | 4676990 | 4824210 | 4736929 | 5166275 | 5166275 | 5166275
Movement in risk | 2143064 | 172169 | 489285 | 342065 | 429346 | 0 | 0 | 0
Previous year's forecast repair risK (x106) | [8 empty] | Variance from previous year (x106) | [8 empty] | % Variance from previous year
| Actuals |  |  |  | Current year actuals | Forecast |  |  |  | Actuals |  |  | Current year actuals | Forecast |  |  |  |  | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Annual repair risk | 3023211 | 4994106 | 4676990 | 4824210 | 4907961 | 4907961 | 4907961 | 4907961 | Annual repair risk | 0 | 0 | 0 | 0 | -171032 | 258314 | 258314 | 258314 | Repair risk reduction | 0% | 0% | 0% | 0% | -3.485% | 5.263% | 5.263% | 5.263%
Movement in risk | 2143064 | 172169 | 489285 | 342065 | 258314 | 258314 | 258314 | 258314 | Movement in risk | 0 | 0 | 0 | 0 | 171032 | -258314 | -258314 | -258314
Safety - Emergency response - Primary output | Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Total PREs | 144573.5 | 141372.73 | 140519.24 | 149043.44 | 139205.72
(1) Controllable
Number of controlled gas escapes or controlled other gas emergencies reported | 49525.1 | 46739.11 | 45250.88 | 47746.12 | 44446.37
Number of responses within timescale (2 hours) | 49025.87 | 46022.57 | 44692.85 | 47077.93 | 43432.7
Percentage of controlled gas escapes responded to within timescale (2 hours) | 98.99% | 98.47% | 98.77% | 98.6% | 97.72%
(2) Non-controllable
Number of uncontrolled gas escapes or uncontrolled other gas emergencies reported | 85766.89 | 83294.24 | 81088.73 | 86745.37 | 80465.44
Number of responses within timescale (1 hour) | 83978.26 | 81297.47 | 79414.52 | 84886.52 | 78116.13
Percentage of uncontrolled gas escapes responded to within timescale (1 hour) | 97.91% | 97.6% | 97.94% | 97.86% | 97.08%
Proportion of gas escapes prevented within 12 hrs (secondary deliverable) | 50% | 54% | 51.8% | 46.97% | 49.09%
Gas in Buildings (GIB) events - Iron mains - Secondary deliverable | Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
GIB events reportable under RIDDOR ie GIB >= 20% LEL or > 10kg from spun/cast iron fracture or DI corrosion of mains of: | 0.18 | 1.09 | 1 | 0 | 0.27 | 0 | 0 | 0
GIB events (any % level) from spun/cast iron fracture or DI corrosion of mains of: | 74.34 | 123.06 | 89.24 | 100.87 | 110.69
Cast/spun iron fractures and ductile iron corrosion failures - Secondary deliverable | Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Number of spun/cast iron fracture or DI corrosion of mains of: | 999.45 | 1213.42 | 982.51 | 1246.05 | 1061.93 | 1130.9445 | 1108.3256 | 1086.1591
Sub-deduct networks - secondary deliverable | Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
% off sub-deduct networks taken of risk | 50% | 28% | 5% | 2% | 2% | 7% | 6% | 6%
Cumulative | 50% | 78% | 83% | 85% | 87% | 94% | 100% | 106%
Note on A71: Ofgem: Any concentration level at any location in the building. Data to include all GIB instances including those reportable under RIDDOR

## 2.5 Reliability
Regulatory Reporting Pack
Cadent East of England
2017/18
2.5 Summary of reliability outputs and secondary deliverables
Summary of loss of supply volumes and duration - primary output
Actual/forecast loss of supply volumes (no.)
| Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
No. of planned interruptions | 75537.2 | 74460 | 76135 | 66502 | 66895 | 73668 | 82157 | 70580 | 585934.2
No. of unplanned interruptions | 15718.16 | 12451.4 | 13451.38 | 20089.14 | 12310.89 | 11776 | 11663 | 11550 | 109009.97
Total interruptions | 91255.36 | 86911.4 | 89586.38 | 86591.14 | 79205.89 | 85444 | 93820 | 82130 | 694944.17
Previous year forecast loss of supply volumes (no.) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals |  |  |  | Current year actuals | Forecast |  |  |  |  | Actuals |  |  | Current year actuals | Forecast | [5 empty] | Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
No. of planned interruptions | 75537.2 | 74460 | 76135 | 66502 | 68274 | 75008 | 75008 | 75008 | 585932.2 | No. of planned interruptions | 0 | 0 | 0 | 0 | -1379 | -1340 | 7149 | -4428 | 2 | No. of planned interruptions | 0% | 0% | 0% | 0% | -2.02% | -1.786% | 9.531% | -5.903% | 0.0003413%
No. of unplanned interruptions | 15718.16 | 12451.4 | 13451.38 | 20089.14 | 12277 | 12025 | 11777 | 11533 | 109322.08 | No. of unplanned interruptions | 0 | 0 | 0 | 0 | 33.89 | -249 | -114 | 17 | -312.11 | No. of unplanned interruptions | 0% | 0% | 0% | 0% | 0.276% | -2.071% | -0.968% | 0.1474% | -0.2855%
Total interruptions | 91255.36 | 86911.4 | 89586.38 | 86591.14 | 80551 | 87033 | 86785 | 86541 | 695254.28 | Total interruptions | 0 | 0 | 0 | 0 | -1345.11 | -1589 | 7035 | -4411 | -310.11 | Total interruptions | 0% | 0% | 0% | 0% | -1.67% | -1.826% | 8.106% | -5.097% | -0.0446%
Final proposals allowed loss of supply volumes (no.) | [9 empty] | Variance from final proposals | [9 empty] | Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
No. of planned interruptions | 585934 | [8 empty] | No. of planned interruptions | 0.2 | [8 empty] | No. of planned interruptions | 3.413e-05%
No. of unplanned interruptions | 99608 | [8 empty] | No. of unplanned interruptions | 9401.97 | [8 empty] | No. of unplanned interruptions | 9.439%
Total interruptions | 685542 | [8 empty] | Total interruptions | 9402.17 | [8 empty] | Total interruptions | 1.371%
Actual/forecast loss of supply duration (mins - million of)
| Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Dur. of planned interruptions | 30.5269 | 27.8309 | 26.6024 | 22.632 | 21.6614 | 27.3016 | 30.4477 | 26.1576 | 213.1606
Dur. of unplanned interruptions | 13.6 | 14.4485 | 10.398 | 60.2005 | 14.6335 | 15.6 | 15.6 | 15.6 | 160.0805
Total interruptions | 44.1269 | 42.2794 | 37.0004 | 82.8325 | 36.295 | 42.9016 | 46.0477 | 41.7576 | 373.2412
Previous year forecast loss of supply duration (mins - million of) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals |  |  |  | Current year actuals | Forecast |  |  |  |  | Actuals |  |  | Current year actuals | Forecast | [5 empty] | Actuals |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Dur. of planned interruptions | 30.5269 | 27.8309 | 26.6024 | 22.632 | 24.6 | 27 | 27 | 27 | 213.1922 | No. of planned interruptions | 0 | 0 | 0 | 0 | -2.9386 | 0.30165 | 3.4477 | -0.84237 | -0.03158 | No. of planned interruptions | 0% | 0% | 0% | 0% | -11.95% | 1.117% | 12.77% | -3.12% | -0.01481%
Dur. of unplanned interruptions | 13.6 | 14.4485 | 10.398 | 60.2005 | 8.2 | 7.9 | 7.6 | 7.3 | 129.647 | No. of unplanned interruptions | 0 | 0 | 0 | 0 | 6.4335 | 7.7 | 8 | 8.3 | 30.4335 | No. of unplanned interruptions | 0% | 0% | 0% | 0% | 78.46% | 97.47% | 105.3% | 113.7% | 23.47%
Total interruptions | 44.1269 | 42.2794 | 37.0004 | 82.8325 | 32.8 | 34.9 | 34.6 | 34.3 | 342.8392 | Total interruptions | 0 | 0 | 0 | 0 | 3.495 | 8.0016 | 11.4477 | 7.4576 | 30.4019 | Total interruptions | 0% | 0% | 0% | 0% | 10.66% | 22.93% | 33.09% | 21.74% | 8.868%
Final proposals allowed loss of supply duration (mins - million of) | [9 empty] | Variance from final proposals | [9 empty] | Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
Dur. of planned interruptions | 213 | [8 empty] | No. of planned interruptions | 0.16063 | [8 empty] | No. of planned interruptions | 0.07541%
Dur. of unplanned interruptions | 108 | [8 empty] | No. of unplanned interruptions | 52.0805 | [8 empty] | No. of unplanned interruptions | 48.22%
Total interruptions | 321 | [8 empty] | Total interruptions | 52.2412 | [8 empty] | Total interruptions | 16.27%
Summary of telemetered faults - secondary deliverables
Actual/forecast telemetered faults (fault * duration/no. of telemetered AGIs - "now faults" (hrs))
| Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Telemetered faults | 70 | 80.37 | 34.09 | 50.37 | 27 | 32 | 31 | 31 | 355.83
Previous year forecast telemetered faults (fault * duration/no. of telemetered AGIs - "now faults" (hrs)) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals |  |  |  | Previous year forecast | [5 empty] | Actuals |  | Current year actuals | Forecast | [6 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Telemetered faults | 70 | 80.37 | 34.09 | 50.37 | 33 | 32 | 31 | 31 | 361.83 | Telemetered faults | 0 | 0 | 0 | 0 | -6 | 0 | 0 | 0 | -6 | Telemetered faults | 0% | 0% | 0% | 0% | -18.18% | 0% | 0% | 0% | -1.658%
Final proposals allowed telemetered faults (fault * duration/no. of telemetered AGIs - "now faults" (hrs)) | [9 empty] | Variance from final proposals | [9 empty] | % Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
Telemetered faults | 127 | 123 | 119 | 116 | 112 | 108 | 105 | 101 | 911 | Telemetered faults | -57 | -42.63 | -84.91 | -65.63 | -85 | -76 | -74 | -70 | -555.17 | Telemetered faults | -44.88% | -34.66% | -71.35% | -56.58% | -75.89% | -70.37% | -70.48% | -69.31% | -60.94%
Summary of pressure systems safety regulations (PSSR) faults - secondary deliverables
Actual/forecast PSSR faults (faults as a % of inspections - PSSR A1 and A2 faults or faults/No. of AGIs - PSSR A1 and A2 faults (delete as appropriate))
| Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
PSSR faults (% or No.) | 5% | 5.44% | 6.681% | 10.42% | 7.5% | 6.085% | 5.542% | 5%
Previous year forecast PSSR faults (faults as a % of inspections - PSSR A1 and A2 faults or faults/No. of AGIs - PSSR A1 and A2 faults (delete as appropriate)) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals |  |  |  | Previous year forecast | [5 empty] | Actuals |  |  | Current year actuals | Forecast | [5 empty] | Actuals |  |  | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
PSSR faults (% or No.) | 5% | 5.44% | 6.681% | 10.42% | 8.797% | 6.085% | 5.542% | 5% |  | PSSR faults (% or No.) | 0 | 0 | 0 | 0 | -0.012965 | 0 | 0 | 0 |  | PSSR faults (% or No.) | 0% | 0% | 0% | 0% | -14.74% | 0% | 0% | 0%
Final proposals allowed PSSR faults (faults as a % of inspections - PSSR A1 and A2 faults or faults/No. of AGIs - PSSR A1 and A2 faults (delete as appropriate)) | [9 empty] | Variance from final proposals | [9 empty] | % Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
PSSR faults (% or No.) | 8% | 8% | 7% | 6% | 6% | 6% | 5% | 5% | 51% | PSSR faults (% or No.) | -0.03 | -0.025598 | -0.0031924 | 0.044236 | 0.015 | 0.00084718 | 0.0054236 | 0 |  | PSSR faults (% or No.) | -37.5% | -32% | -4.561% | 73.73% | 25% | 1.412% | 10.85% | 0%
Number and value of offtake meter error reports
| Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Volume of offtake meter errors (GWh) | 2 | 2 | 0.82 | 26.8139 | 0 | 0 | 0 | 0
Throughput (GWh) | 521.6 | 97396 | 95748 | 98709.598 | 104129 | 103067 | 103023 | 102408
Meter errors/throughput (%) |  |  | 0.0008564% | 0.02716% | 0% | 0% | 0% | 0%
Summary Capacity Utilisation
Capacity utilisation | Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
</= 50% | 83 | 82 | 106 | 103 | 140 | 141 | 141 | 141
>50% to </=70% | 89 | 92 | 89 | 95 | 63 | 62 | 62 | 62
>70% to </=80% | 49 | 47 | 41 | 41 | 23 | 23 | 23 | 23
>80% to </=100% | 45 | 45 | 31 | 30 | 44 | 44 | 44 | 44
>100% | 11 | 11 | 10 | 8 | 7 | 7 | 7 | 7
Total no. of sites | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277

## 2.6 Environmental
Regulatory Reporting Pack
Cadent East of England
2017/18
2.6 Summary of environmental outputs - shrinkage and leakage volumes
Actual/forecast shrinkage volumes (GWh)
| Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Shrinkage volumes at start of RIIO-GD1 | 517.4
Shrinkage volume | 478.1 | 465.0934 | 449.3995 | 449.7277 | 439.9077 | 428 | 411 | 395
Shrinkage baselines | 529.4 | 515 | 503 | 490 | 479 | 467 | 455 | 444
Shrinkage volume reduction | 39.3 | 52.3066 | 68.0005 | 67.6723 | 77.4923 | 89.4 | 106.4 | 122.4
% shrinkage volume reduction | 7.596% | 10.11% | 13.14% | 13.08% | 14.98% | 17.28% | 20.56% | 23.66%
Previous year forecast shrinkage volumes (GWh) | [8 empty] | Variance from previous year | [8 empty] | % Variance from previous year
| Actuals |  |  |  | Previous year forecast |  |  |  |  | Actuals |  |  | Current year actuals | Forecast |  |  |  |  | Actuals |  |  | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Shrinkage volumes at start of RIIO-GD1 | 517.4
Shrinkage volume | 478.1 | 465.0934 | 449.3995 | 449.7277 | 446.1377 | 428.1347 | 410.7456 | 394.5676 | Shrinkage volume | 0 | 0 | 0 | 0 | -6.23 | -0.13471 | 0.25442 | 0.43237 | Shrinkage volume | 0% | 0% | 0% | 0% | -1.396% | -0.03146% | 0.06194% | 0.1096%
Shrinkage volume reduction | 39.3 | 52.3066 | 68.0005 | 67.6723 | 71.2623 | 89.2653 | 106.6544 | 122.8324 | Shrinkage volume reduction | 0 | 0 | 0 | 0 | 6.23 | 0.13471 | -0.25442 | -0.43237 | Shrinkage volume reduction | 0% | 0% | 0% | 0% | 8.742% | 0.1509% | -0.2385% | -0.352%
% shrinkage volume reduction | 7.596% | 10.11% | 13.14% | 13.08% | 13.77% | 17.25% | 20.61% | 23.74%
Final proposals allowed shrinkage volumes (GWh) | [8 empty] | Variance from final proposals | [8 empty] | % Variance from final proposals
| Final proposals | [8 empty] | Final proposals | [8 empty] | Final proposals
Shrinkage volume reduction | 15.3% | [7 empty] | Shrinkage volume reduction | 43.2378 | [7 empty] | Shrinkage volume reduction | 8.357%
Actual/forecast leakage volumes (GWh)
| Actuals |  |  |  | Current year actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Leakage volumes at start of RIIO-GD1 | 481.6
Leakage volume | 451 | 434.8073 | 419.5279 | 418.8452 | 408.829 | 397 | 380 | 364
Leakage baselines | 495.5 | 482 | 470 | 458 | 447 | 435 | 423 | 412
Leakage volume reduction | 30.6 | 46.7927 | 62.0721 | 62.7548 | 72.771 | 84.6 | 101.6 | 117.6
% Leakage volume reduction | 5.914% | 9.716% | 12.89% | 13.03% | 15.11% | 17.57% | 21.1% | 24.42%
Previous year forecast leakage volumes (GWh) | [8 empty] | Variance from previous year | [8 empty] | % Variance from previous year
| Actuals |  |  |  | Previous year forecast |  |  |  |  | Actuals |  |  | Current year actuals | Forecast |  |  |  |  | Actuals |  |  | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Leakage volumes at start of RIIO-GD1 | 481.6
Leakage volume | 451 | 434.8073 | 419.5279 | 418.8452 | 414.7429 | 396.9295 | 379.567 | 363.7381 | Leakage volume | 0 | 0 | 0 | 0 | -5.9139 | 0.070529 | 0.43304 | 0.26186 | Leakage volume | 0% | 0% | 0% | 0% | -1.426% | 0.01777% | 0.1141% | 0.07199%
Leakage volume reduction | 30.6 | 46.7927 | 62.0721 | 62.7548 | 66.8571 | 84.6705 | 102.033 | 117.8619 | Leakage volume reduction | 0 | 0 | 0 | 0 | 5.9139 | -0.070529 | -0.43304 | -0.26186 | Leakage volume reduction | 0% | 0% | 0% | 0% | 8.846% | -0.0833% | -0.4244% | -0.2222%
% Leakage volume reduction | 5.914% | 9.716% | 12.89% | 13.03% | 13.88% | 17.58% | 21.19% | 24.47%
Final proposals allowed leakage volumes (GWh) | [8 empty] | Variance from final proposals | [8 empty] | % Variance from final proposals
| Final proposals | [8 empty] | Final proposals | [8 empty] | Final proposals
Leakage volume reduction | 15.9% | [7 empty] | Leakage volume reduction | 41.0256 | [7 empty] | Leakage volume reduction | 8.519%
Note on B23: revised baseline based on lastest shrinkage/leakage model - informed as part of the SQ process
Note on B49: revised baseline based on lastest shrinkage/leakage model - informed as part of the SQ process

## 2.7 Performance Snapshot
Regulatory Reporting Pack
Cadent East of England
2017/18
2.7 Performance Snapshot
Network |  |  | Actual 2017/18
Number of customers directly connected to network | No. | Comparator | 4011238.5
Total GDN network length all pressure tiers | km | Comparator | 51780.3259
Network reliability
Overall network reliability | % of full delivery 24/7/365 | Comparator | 100%
Unplanned customer interruptions - exc major incidents | No. of customers affected | Comparator | 11762.89
| % per number of total customers | Comparator | 0.2932%
| Average duration in minutes | Comparator | 1054.6822
Number of major incidents | Number : Customers Effected | Comparator | 1 : 548
Customer Satisfaction
Customer Satisfaction - unplanned interruptions | score out of 10 | Ofgem target (8.01) | 9.4427
Customer Satisfaction - planned interruptions | score out of 10 | Ofgem target (8.04) | 8.4621
Customer Satisfaction - connections | score out of 10 | Ofgem target (8.09) | 8.4371
Complaints metric | scoring of complaints resolution | Ofgem target - need to be below 11.57 | 5.7085
Connections
% of all quotes issued within timescales set | % | Ofgem target | 99.74%
% of jobs substantially completed on date agreed with the customer | % | Ofgem target | 93.66%
Social Obligations
Fuel Poor Connections made in year | No. | Ofgem target | 1921
% of fuel poor connections RIIO to date vs period to date target | % better than target | Comparator | 28.68%
Safety
Attend Uncontrolled escape in 1 hr | % achieved | Ofgem target is 97% | 97.08%
Attend Controlled escape in 2 hrs | % achieved | Ofgem target is 97% | 97.72%
Annual repair risk performance vs target | % better than target | Ofgem target | 91.69%
Iron mains risk removed | % better than target | Ofgem target | 98.76%
Environmental Impact
Reduction in shrinkage in year (gas emmissions) | Volume (GWh) | Comparator | -3.59
Shrinkage actuals compared to target volume | Improved shrinkage % | Ofgem target | 8.357%
Renewable gas connections | Number : Volume (scmh) | Comparator | 0 : 1230
Financials
Totex operating costs | £m | Ofgem Target | 319.467
% lower Totex than allowance | % | Comparator | 8.916%
Other pass through costs | £m | Comparator | 122.6681